## Sheet1
Release	Priority	Done	Area	Description
0.4.1	5	1	IrTrans	IrTrans command teaching.
0.4.1	5	1		Website update
0.4.1	10	1	UI	Change window system so that both UI have separate windows.
0.4.1	10	1	UI	Fullscreen mode.
0.4.1	11	1	RELEASE	Release 0.4.1
0.4.2	15	1	UI	Rename remote feature.
0.4.2	15	1	IrTrans	IrTrans command editor & relearn
0.4.2	15	1	Irreco	Grid background images.
0.4.2	19	1	RELEASE	Release 0.4.2
0.4.3	20	1	IrTrans	IrTrans new command shows dialog once per command
0.4.3	20	1	LIRC	Improve LIRC backend error codes.
0.4.3	20	1	LIRC	Cleanup LIRC backend.
0.4.3	29	1	RELEASE	Release 0.4.3
0.4.4	30	1	Irreco	Layout background images.
0.4.4	39	1	RELEASE	Release 0.4.4
0.4.5	40	1	IrTrans	Autodetect for IrTrans devices
0.4.5	49	1	RELEASE	Release 0.4.5
0.5.0	50	1	Irreco	Source project splitting.
0.5.0	51	1	Irreco	Separate Device configuration dialog
0.5.0	51	1	Backend	Delete backend configuration file when backend is deleted.
0.5.0	59	1	RELEASE	Release 0.5.0
0.5.1	10	1	Irreco	Bug fixing and ui tweaks
0.5.1	20	1	RELEASE	Release 0.5.1
0.5.2	10	1	UI	Build system which allows user to map N800 faceplate buttons to commands.
0.5.2	10	1	IrTrans	Support for remote irserver. Test with IrTrans USB dongle and Linux PC.
0.5.2	30	1	RELEASE	Release 0.5.2
0.5.3	20	1	Irreco	Command execution rate selection.
0.5.3	70	1	Irreco	OS2008 support.
0.5.3	79	1	RELEASE	Release 0.5.3
0.5.4	10	0	Irreco	Restructure IrrecoCmd to use Gobject inheritance instead of switch case mess
0.5.4	15	0	Irreco, UI	Support for command repeat while button is pressed.
0.5.4	30	0	Irreco	Restructure buttonstyles into IrrecoButtonStyleManager
0.5.4	35	0	Irreco	Implement theme sorting to IrrecoButtonStyleManager
	100	0	RELEASE	Release 0.5.4
0.5.5	15	0	UI	Add show name checkbox to the button dialog.
0.5.5	70	0	UI	Build better Backend error dialog.
0.5.5	70	0	Irreco	valgrind testing
0.5.5	70	0	UI	Create visual error messageboxes.
	80	0	Backend	Create command line backend.
	80	0	Backend	Create ssh command line backend.
	90	0	Irreco	Show button location even if the image is invisible.
	90	0	Irreco	Button rotation
	99	0	Config	Save snap to grid value somewhere.
	899	0	Irreco	Video user quide.
	899	0	Backend	Create Web browser backend. Telkku.com
	999	0	Ir Conversion	Implement
	999	0	Lirc IrTrans	Lirc remote config library support, somehow
	999	0	Irreco	Larger remote controllers than display, with touch scrolling.
	999	0	Irreco	Kinetic scrolling / switching of remotes
	999	0	Irreco	gradient background color
	999	0	Irreco	Plan and implement Dbus api for backends
	999	0	Irreco	Use g_log to debug, instead of IRRECO_* macros.
	999	0	Layout	System for importing / exporting button layout
	999	0	Irreco	Doxygen documentation
	999	0	Ir Database	Implement, lircwebise, remotecentral
	999	0	X10	Implement
	999	0	Backend	System for importing / exporting backend configurations.

## Sheet2
	0.5		Assigned
	Arto	Jussi	Arto
		4	Arto	Jussi
5	1		Arto	Arto	Website update
15				Arto
20			Arto
			Arto
			Arto
20
20	1	4		Release 0.6
					Release 0.5
20

99
99
99

15		IrTrans	Jussi	Support for remote irserver. Test with IrTrans USB dongle and Linux PC.

16			IrTrans		IrTrans command teaching.